Computational Molecular Biology Projects 2006

Deliverables:

- Implementation

- 3 presentations: basics, literature, demo (a schedule will be developed later)

Deadlines (may be disrupted on guest lectures/important discussions):

Presentation on basics: 45 minutes

- March 14:	Protein-protein interaction (JN, CR)

<a href=”???”>presentation</a>

- March 21:	System Biology and the E-coli paper (WH, GH)

<a href=”Systems Biology 1.ppt”>presentation</a>

- March 28: 	Protein structures and classifications (SJ, KC)

<a href=”ProteinDockingPresentation1.pdf”>presentation</a>

Presentation on current trends and literature: 45 minutes

- April 4:	Structure comparison algorithms, project design (SJ, KC)

<a href=”ProteinClassfyPresentation2.ppt”>presentation</a>

- April 11:	System biology (WH, GH)

<a href=”SystemsBio2.ppt”>presentation</a>

- April 18:	Protein Docking, project algorithms and experiment design (JN, CR)

<a href=”CurrentDockingResearch-2.pdf”>presentation</a>

April 25-27: Individual status report from each group (1/2 hr each group each day)

Final Project Presentation: 1 hour each group

May 2: 7:30 – 10:30 pm, Room: TBD

Protein Docking

(Johannes Nangolo & Christopher Roach)

- Implement the alignment algorithm and test with synthetic data: Due March 21

- Download proteins (>4) of similar structures and extract their backbone chain coordinates:	Due April 4

- Find and verify local alignments, organize results quantitatively

- Present protein docking literature (>4 seminal papers + basics)

Sequence comparison

(Steve Johnson & Kyle Cacciatore)

- Download proteins (>9) of similar and dissimilar structures: Due March 28

- Familiarize/modify code of  “correlogram-based” method of sequence comparison (Mitra-Samant 2005):	Due April 4

- Run and verify structural similarity detection capability of the algorithm, organize results quantitatively

- Present protein structure-classification fundamentals

http://www.cs.fit.edu/~dmitra/Compbio/06Spr.d/GandhaliSamant_Thesis(1).ppt

http://www.cs.fit.edu/~dmitra/Pub/MitraSamant-iea06Camready.pdf

Resources common to the two above projects:

- http://www.ebi.ac.uk/dali/

- http://cathwww.biochem.ucl.ac.uk/latest/index.html

- http://scop.mrc-lmb.cam.ac.uk/scop/

- http://www.rcsb.org/pdb/Welcome.do

E-coli DNA replication simulation

(Weijen Huang & Gary Herzo)

- Study DNA replication modeling technique (Joseph M. Mahaffy, and Judith W Zyskind, J. Theoretical Biol. 1989)

- Familiarize with the existing GUI for simulation

- Extend the GUI with the modeling capability: Due March 21

- Extend the model with Leonard et al’s results: Due April 4

- Embed the new model in the GUI

- Present temporal modeling in system biology (>1 seminal papers)

- http://www.cs.fit.edu/~dmitra/Compbio/06Spr.d/e-coli model.ppt

http://www.cs.fit.edu/~dmitra/Compbio/06Spr.d/ecoli-equations.doc

Single Nucleotide Polymorphism phylogeny construction

(Manuel Alejo)

- Study and present statistical sequence comparison basics

- Find and present how to develop phylogeny for SNP data using PHYLIP package from U of Washington

- Run appropriate Phylip software to develop phylogeny for given mouse SNP data (I will supply), some preprocessing may be needed